## Gantt Chart
Tasks | Start Date | Days Needed | Completion | Adjusted Lenght
Miro Architecture Diagram | 2025-10-01 | 3 | 2025-10-06 | 6
Cleaned CSV Dataset | 2025-10-03 | 5 | 2025-10-10 | 7
Processed Snowflake Table | 2025-10-03 | 3 | 2025-10-08 | 3
Data Visualation | 2025-10-04 | 5 | 2025-10-10 | 5
CEO Presentation | 2025-01-09 | 1 | 2025-01-10 | 4
Final Submission | 2025-10-12 | 3 | 2025-10-15 | 1
Formulas:
Completion = WORKDAY([Start Date],[Days Needed])